## Slide 1: Autonomous Underwater Vehicle (AUV) Prototype Phase I and II Proposals by: SOLUTIONS
Thomas Green, Thanh Vo, Jordan Hiroshima, Jessica Sahr

## Slide 2: Agenda
Proposal Overview
CONOPs
WBS/Statement of Work
Critical Path Network
Schedule
Cost Estimate
Notes: Fix formatting

## Slide 3: Proposal Overview
Option | Phase I – Base | Phase II – Option
Scope | Perform concept demo for production representative prototype | Design finalization (EMD) and production LRIP/FRP
Key Deliverables: | Concept Demo Qty 1 Production Representative Prototype | Qty 42 (Qty 6 LRIP, Qty 36 FRP)
PoP: | 12 months | EMD: 6 months Production: 18 months
Contract Type: | CPFF LOE/CPFF | CPFF/FFP
Proposal $ | $8,210,225 | $17,914,050

## Slide 4: Top Level Specifications
Parameter | Value
Length | 3m
Diameter | 400mm
Weight | 100kg
Operational Depth | 5ft to 200ft
Range | 5 miles
Speed | 3 knots
T3 AUV can complete all missions
  Surveillance and reconnaissance
  Recovery of reusable underwater targets
  Attached recovery lines to various objects
Designed to operate autonomously; manual override
  Ultra-high frequency on surface
  Low frequency while submerged
AUV communication
  Communication will be encrypted for production
  Demonstrations will be unencrypted

## Slide 5: Top Level Specifications
Top Level | WBS | Specification | SOW
Systems Engineering | 1.2 | System Engineering Management Plan Test and Evaluation Management Plan Configuration Item Requirement Specifications Technical Reviews | 3.2.1 3.2.2 3.2.3 3.2.4
Hardware Engineering | 1.3 | Propulsion and Steering Sensor Payload Manipulator Communication Module Ultra-High Frequency Radio Low Frequency Radio Modulator/Demodulator AUV Controller Structural Housing Launch and Recovery System | 3.3.1.1 3.3.1.2 3.3.1.3 3.3.1.4 3.3.1.4.1 3.3.1.4.2 3.3.1.4.3 3.3.1.5 3.3.1.6 3.3.1.7
Software Engineering | 1.4 | Mission Planning Software AUV Control Software Data Analysis Software | 3.3.3.1 3.3.3.2 3.3.3.3
Integration & Test | 1.6 | Module Level Testing System Integration Demonstrations | 3.3.5
All requirements understood and covered under WBS and SOW

## Slide 6: CONOPs
Transport to Area
of Operations
Load Mission Parameters
Perform Mission
Offload Sensor Data, etc;
Data Analysis
Freshwater Washdown &
Maintenance
Transport to Base
Storage
Basic AUV
CONOPS

## Slide 7: Work Breakdown Structure
Example to Tier 4 for Software
1.4. Software (SW) Engineering
1.4.1. AUV Software
1.4.1.1. Navigation
1.3.1.2. Propulsion & Steering Ctrl
1.4.1.2. Sensor Op & Data Collection
1.4.1.3. Communication
1.4.1.4. "Target" Acquisition & Posit
1.4.1.5. Manipulator Operation
1.4.1.6. Manual Override
1.4.2. Mission Planning SW
1.4.2.1. GIS Maps
1.4.2.2. Mission Parameters
1.4.3. Data Analysis SW
1.4.3.1. Imagery Analysis
1.4.3.3. Navigation Model Update

## Slide 8: Statement of Work (SOW)
Program Management
Systems Engineering
Hardware Engineering
Software Engineering
Specialty Engineering, e.g.
  Reliability
  Structural Modeling
Support & Training
Integration & Test
The Statement of Work covers the following development activities:

## Slide 9: SOW – Program Management
Monthly Status Review
Monthly Status Report
Program Management Reviews
Integrated Master Schedule
Quality Management
Configuration & Data Management

## Slide 10: SOW – Systems Engineering
Systems Engineering Management Plan (SEMP)
Test Engineering Management Plan (TEMP)
Requirement Specifications for all hardware and software configuration items
Systems Engineering Technical Reviews
  System Functional Review
  Preliminary Design Review
  Demonstration Test Readiness Review

## Slide 11: SOW – Hardware Engineering
Trade studies and selection of:
  Motor, Battery, Servomotors for propulsion system
  Sonar, Infrared, Optical and Inertial Navigation sensors
  Radios for communication module
  Autonomous Controller
Development/Integration of:
  Propulsion system
  Payload (sensor) module
  Communication module
  Controller
  Manipulator
  Structural housing
  Transport, launch and recovery system (adapted from existing hardware)

## Slide 12: SOW – Software Engineering
Development/Integration of:
  AUV software
    Navigation
    Propulsion & Steering Control
    Sensor Operation & Data Collection
    Communication
    Target Acquisition & Positioning
    Manipulator Operation
    Manual Override
  Mission Planning Software
    GIS Map Loading
    Geofencing
    Mission Parameters
  Data Analysis Software
    Imagery Analysis
    Navigation Model Updates
    Target Acquisition Model Updates
    Sensor Analysis

## Slide 13: SOW – Integration & Test
Individual Module Testing (w/ Controller):
Sensor Testing
Propulsion & Navigation Testing
Manipulator Testing
Communication Testing
Integrated System Testing:
Full System Test – Dry
Full System Test – Wet
Demonstration Dry Run
Operational Demonstration

## Slide 14: Critical Path Network

## Slide 15: Gantt Chart
Phase I

## Slide 16: Gantt Chart
Phase II

## Slide 17: Schedule
Phase I PoP is 12 months, Phase II PoP is 24 months

## Slide 18: Cost Estimate
Project Name:
  Autonomous Underwater Vehicle (AUV) Prototype
Project Phases:
  Phase I – Fully operational prototype development & demonstration
  Phase II – Finalized design, transition to low-rate initial production (LRIP) & full-rate production (FRP)
Contract Type:
  CPFF @ 10% Fee
Project Value:
  Phase I - $8,210,225
  Phase II - $17,914,050
Project Duration:
  Phase I – 1 January 2024 – 3 January 2025 (12 months)
  Phase II – 6 January 2025 – 1 January 2027 (24 months)
Phase I | Material | Labor | Travel | Test Equipment | Manufacturing Facility & Equipment
Sub-Total | $ 543,900 | $ 5,669,800 | $ 341,050 | $ 1,000,000 | $ -
Total Cost |  |  |  |  | $ 8,210,225
Phase II | Material | Labor | Travel | Test Equipment | Manufacturing Facility & Equipment
Sub-Total | $ 747,500 | $10,778,000 | $ 260,000 | $ 500,000 | $ 4,000,000
Total Cost |  |  |  |  | $ 17,914,050