## Labor
Title | Pct Time | Weeks | Rate (Hr) | Rate (Wk) | Total
Program Manager | 100% | 52 | 225 | 9000 | 468000
Scheduler - Initial | 100% | 2 | 150 | 6000 | 12000
Scheduler - Ongoing | 10% | 40 | 150 | 6000 | 240000
Cost Account Manager | 25% | 52 | 150 | 6000 | 312000
Lead Systems Engineer (SE) | 25% | 52 | 200 | 8000 | 416000
Requirements SE | 100% | 4 | 150 | 6000 | 24000
Test Engineer 3 | 20% | 52 | 150 | 6000 | 312000
Mechanical Engineer 4 | 100% | 52 | 180 | 7200 | 374400
Mechanical Engineer 3 | 100% | 52 | 150 | 6000 | 312000
Structural Engineer (Analysis) | 100% | 4 | 200 | 8000 | 32000
Electrical Engineer 4 | 100% | 52 | 180 | 7200 | 374400
Electrical Engineer 3 | 50% | 52 | 150 | 6000 | 312000
Sensor Specialist 4 | 100% | 12 | 180 | 7200 | 86400
RF Engineer 4 - Initial | 100% | 12 | 180 | 7200 | 86400
RF Engineer 4 - Ongoing | 20% | 40 | 180 | 7200 | 288000
Embedded HW Engineer 4 - Initial | 100% | 36 | 180 | 7200 | 259200
Embedded HW Engineer 4 - Ongoing | 20% | 16 | 150 | 6000 | 96000
Senior SW Engineer | 50% | 52 | 200 | 8000 | 416000
SW Engineer 4 | 100% | 40 | 180 | 7200 | 288000
SW Engineer 3 | 100% | 40 | 150 | 6000 | 240000
Database Engineer | 50% | 12 | 150 | 6000 | 72000
Data Analyst | 50% | 12 | 150 | 6000 | 72000
Reliability Engineer | 20% | 8 | 180 | 7200 | 57600
Quality Assurance Engineer | 20% | 52 | 180 | 7200 | 374400
Mission Analyst | 50% | 12 | 180 | 7200 | 86400
Configuration Manager | 25% | 52 | 150 | 6000 | 312000
Subcontract Administrator | 20% | 52 | 150 | 6000 | 312000
|  |  |  | Labor | 6235200

## Materials
Description | Unit | Cost/Unit | # Units | Total Cost
Motor | Each | 1200 | 2 | 2400
Battery & Charging | Each | 450 | 2 | 900
Power Distribution (PD) Harness | Each | 320 | 2 | 640
PD Development Materials | Bulk | 200 | 1 | 200
Servomotors | Each | 220 | 4 | 880
Propulsion Module Development Materials | Bulk | 450 | 1 | 450
Sonar Sensor | Each | 800 | 2 | 1600
Infrared Sensor | Each | 450 | 2 | 900
Optical Sensor | Each | 450 | 2 | 900
Inertial Navigation Sensor | Each | 250 | 2 | 500
Sensor Payload Integration Package Materials | Bulk | 340 | 1 | 340
Sensor Interface Board | Each | 350 | 2 | 700
Manipulator | Each | 6800 | 2 | 13600
LF Radio | Each | 250 | 2 | 500
UHF Radio | Each | 250 | 2 | 500
Modem | Each | 200 | 2 | 400
Controller | Each | 480 | 2 | 960
Mission Plannning/Data Analysis PC | Each | 1200 | 2 | 2400
Structural Integration Materials | Bulk | 2500 | 1 | 2500
|  |  | Total | 31270
Could also take into account:
Specialized Test Equipment
Facilities