Work Breakdown Structure, Tier 3 (Tier 4 for SE Tasks)
1. AUV
1.1. Program
Management
1.2. Systems
Engineering
1.3. Hardware Engineering
1.4. Software Engineering
1.5. Support & Training
1.6. Integration & Test
1.7. Operational
Demonstration
1.7.1. Demo Test Plan
1.3.1. Steering
& Propulsion
1.4.1. AUV SW
1.5.1. Tech Manuals
1.6.1. Sensor I&T
1.2.1. SEMP
1.1.1. Tech Reports, Briefs
1.2.2. TEMP
1.7.2. Demo Dry Run
1.3.2. Sensor Payload (Sonar, IR, etc)
1.4.2. Mission Planning SW
1.5.2. Training Manuals
1.6.2. Prop & Navigation I&T
1.1.2. Progress, Status, Mgmt Reports
1.2.3. Req Specifications
1.7.3. Dry Run Review
1.6.3. Manip Testing
1.4.3. Data Analysis SW
1.3.3. Manipulator
1.2.3.1. AUV Spec
1.1.3. Quarterly PMRs
1.7.4. Test Plan Update
1.6.4. Manip Integrated Test
1.2.3.2. Supp Equip Spec
1.3.4. Comms Module
1.1.4. Periodic Cost & Tech Progress Rpts
1.7.5. Op Demonstration
1.6.5. Comms I&T
1.2.4. SE Tech Reviews
1.3.5. Controller
1.1.5. Statement of Work
1.7.6. Op Demonstration Report
1.6.6. Fully Integrated AUV Testing
1.2.4.1. SRR
1.3.6. Ops
Van (Conex Box)
1.1.6. IMS
1.2.4.2. PDR
1.1.7. Risk Analysis & Mgmt Plan
1.3.7. Support Vessel Integration
1.2.4.3. CDR
1.2.4.4. Demo TRR
1.1.8. Periodic & Final Invoices